## Cover Sheet
2020-11-19
System Performance Specification
Project Name: |  | Sign and Line Detection
This documents details all requirements which apply to the system. All items are listed with Title, Description, Status etc. This document is updated on weekly basis enlisting item performed during the week.
Document updates:
Sl Nr./ Version | Title | Short description of changes | Author | Date
1 | Draft | Initial version | Vivek Subramonian | 2020-11-11
2 | Draft | Making the requirements more atomic that is splitting down the requirements. | Vivek Subramonian | 2020-11-19
3 | Draft | Marking the priority and functionality of all the requirements | Vivek Subramonian | 2020-12-01
4 | Draft | Addition of Use cases | Vivek Subramonian | 2020-12-24
5 | Draft | Updation of Status in the requirements documents | Vivek Subramonian | 2021-01-02
6 | Draft | Addition of final requirements in the requirements documents. | Vivek Subramonian | 2021-01-11
7 | Final | Freezing of Requirements and use cases. | Vivek Subramonian

## System Specification
The system in the requirement sheet refers to a computer with the following specifications: Evaluation board: A raspberry pi 4 RAM and Memory: 8GB and 64GB Operating System: Raspbian OS Software used: Python with Opencv and Tensorflow modules.

## Requirements
Requirement Specifications:
Priority definition: Priotity is defined as the importace level of each requirement specified. 5-4 : Very high Priority (given by Orange). This signifies the basic minimum requirement that must be implemented into the project. 3 : Middle level Priority( given by Yellow). This signifies requirements that can be implemented after higher priority requirements are implemented. 1-2: Low level Priority (given by Blue). This level signifies optional requirements. A definition of system is given on sheet 2.
Req.ID | Feature | Objective/Rationale | Requirement | Use Case ID | Responsibilty | Priority | Functional Req. ? | Associated Test ID | % Maturity | Remark/Status | Domain
REQ-101 | Line Detection(straight lines) | To detect the straight lane lines on the road. Stright lane lines set the boundary of the road, | The system shall detect straight lane lines on either side of the road. Test ID: TE1001, TE1002, TE1013 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1001, TE1002, TE1013 | 100% | Got a working model. Sucessfully detecting our objective which are lane lines. | Main Requirement
REQ-102 | Line Detection(dashed lines) | To detect the dashed lane lines on the road. Dashed lane lines separate the two directions of traffic and it on the middle of the road. | The system shall detect dashed lane lines on the roads. Test ID: TE1001, TE1002, TE1013 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1001, TE1002, TE1013 | 100% | Got a working model. Sucessfully detecting our objective which are lane lines. | Main Requirement
REQ-103 | Region of Interest | To select the region of interest(ROI) from the user. | The system shall support user-defined Region Of Interest(ROI) selection through a text based input. Test ID: TE1005, TE1017 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1005, TE1017 | 100% | User can input the desired ROI. | Main Requirement
REQ-104 | Selection of Current lane | To detect the lane on which the car is travelling. | The system shall specifically detect the lane which it is travelling. Test ID: TE1003, TE1004,TE1015 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1003, TE1004,TE1015 | 100% | Lane lines have been isolated. | Main Requirement
REQ-105 | Switching lanes | To detect any lane changes when the car switches lanes while in motion. | The system shall detect lane switching, thereby continuing to detect proper lane line even after switching. Test ID: TE1010, TE1023 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1010, TE1023 | 100% |  | Main Requirement
REQ-106 | Narrow lanes | To detect lane lines on a narrow lane. Since some roads in the city tend to be narrow, it’s a very useful feature. | The system shall detect lane line on the road while traversing on narrow lanes of 2.5 to 3.5m. Test ID: TE1010, TE1022 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1010, TE1022 | 100% | Detecting both narrow and wide lanes. | Main Requirement
REQ-107 | Wide lanes | To detect lane lines on a wide lane. Since the roads on highways tend to be broad or wide, its important that the system detect these lane lines. | The system shall detect lane lines on the road while traversing on wide lanes of width 3.75m or more. Test ID: TE1010, TE1022 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1010, TE1022 | 100% | Detecting both narrow and wide lanes. | Main Requirement
REQ-108 | Detection in highways, city and rural roads. | To detect lane lines on roads of highways, city and rural. | The system detect lane lines on highways, city and rural roads. Test ID: TE1006, TE2006 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 5 | Yes | TE1006, TE2006 | 100% | Working well is all manner of roads. | Main Requirement
REQ-109 | Curved lines | To detect lane lines when the road is a has a curved path. | The system shall detect slightly curved lane line on either side of the road. Test ID: TE1012, TE1024 | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 1 | Yes | TE1012, TE1024 | 100% | Able to detect curved lane lines to an extent. But cannot detect extreme curves. Further work required. | Not a main requirement
REQ-110 | Detections under the conditions of shadows | To detect lane lines on the road even in the presence of shadows. | The system's ability to detect lane lines shall now degrade under the influence of shadows. Test ID: TE1018 | __ | __ | 1 | Yes | TE1018 | __ | Detection with the effect of shadows shall be incorporated at a later date when the software is refined. | Not a main requirement
REQ-111 | Detections under the various weather conditions | To detect lane line under the influence of rain, snow, fog, hail etc. | The system shall detect lane lines in all weather conditions such as fog, rain snow, hail etc. Test ID: TE1009 | UC01, UC03, UC04, UC05, UC06, UC07, UC08 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 1 | Yes | TE1009 | __ | Need a video to test. Currently not testable. | Not a main requirement
REQ-112 | Night time detection | To detect lane lines even during night time. | The system shall detect lane lines even during the night. Test ID: T2007, TE1020 | UC01,UC02, UC03, UC04, UC05, UC06 | Juliet Eldo, Saranya Suresh, Shubhaga Kannan | 1 | Yes | T2007, TE1020 | 100% |  | Not a requirement
REQ-201 | Sign Detection | To detect various types of road signs. Roads give information to the driver. Detection refers to capturing of road signs by the camera and classificaiton of signs by the system. | The system shall detect mandatory and precautionary signs on an open straight road. Test ID: TE2001, TE2007 | UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 5 | Yes | TE2001, TE2007 | 100% | Can detect signs based on colours and recognize them but frame rate a bit slow and choppy. Next step to seprate the signs based on shapes. | Main Requirement
REQ-202 | Mandatory Signs (refer sheet 4) | To detect various types of mandatory signs. The various types of mandatory signs are given on sheet 4. | The system shall detect major road signs such as stop sign, turn signs and one way signs. Refer sheet 4 for list of mandatory signs. Test ID: TE2002, TE2004. | UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 5 | Yes | TE2002, TE2004 | 100% |  | Main Requirement
REQ-203 | Pracautionary signs (refer sheet 5) | To detect various types of precautionary signs. The various types of precautionary signs are given on sheet 5. | The system shall detect pracautionary signs such as keep to a lane signs, slow down signs, caution signs and other such signs on any shape of the sign boards. Refer sheet 5 for list of precautionary signs. Test ID: TE2003, TE2008 | UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 3 | Yes | TE2003, TE2008 | 100% |  | Main Requirement
REQ-204 | Multiple signs detection | To detect multiple signs on the road. Multiple road signs refer to when two or more signs are found stacked over each other or next to each other. | The system shall detect mutiple traffic signs on the road. Test ID: TE2005, TE2011 | UC02, UC03, UC04, UC05, UC06, UC07, UC08 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 5 | Yes | TE2005, TE2011 | 100% |  | Main Requirement
REQ-205 | Traffic light signals | To detect digital traffic lights. Not in the scope of our objectives. | The system shall detect traffic light signals on the road. Test ID: TE2009 | __ | __ | 1 | Yes | TE2009 | __ |  | Not a main requirement
REQ-206 | Speed limit signs (from 20-120 Kmph) | To detect speed limit signs. These signs state the speed at which the drive has to travel. | The system shall detect speed limit signs on a particular lane. Test ID: TE2005, TE2010 |  | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 4 | Yes | TE2005, TE2010 | 100% |  | Main Requirement
REQ-207 | Night time detection | To detect road signs even during night time. | The system shall detect signs even during the night. Test ID: T2007, TE1020 | UC01,UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 1 | Yes | T2007, TE1020 | 100% |  | Not a requirement
REQ-208 | Detections under the various weather conditions | To detect road signs under the influence of rain, snow, fog, hail etc. | The system shall detect traffic signs in weather conditions such as in snow, fog, cloudy, rain etc. Test ID: TE2008, TE1021 | UC02, UC03, UC04, UC05, UC06, UC07, UC08 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 1 | Yes | TE2008, TE1021 | __ | Able to detect traffic signs in foggy/snowy/rainy conditions to an extent. | Not a main requirement
REQ-209 | Detection of damaged or faded sign boards | To detect road signs which are damaged or faded such as old sign boards. | The system shall detect damaged or faded sign boards to an accuracy of over 50%. Accuracy refers to the number of signs correctly classified from the frames of the input video. Test ID: TE2012 | UC02, UC03, UC04, UC05, UC06, UC07, UC08 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 2 | Yes | TE2012 | __ | Can extract the colour but not able to classify accurately. | Not a main requirement
REQ - 301 | Modularity and portability | Modularity and protability are one of the main features of embeded systems. | The system shall be modular and portable to fit in all major sizes of car. | __ | Sayli Deshmukh and Vivek Subramonian | 5 | Non Functional | __ | 100% | Further setup for mounting required. | Hardware Requirement
REQ - 302 | Camera | A camera mounted on the car is required to capture video from the road so as to detect lane lines and signs. | The camera used in the system shall capture at the rate of 24 frames per second. Test ID: TE3001, TE1004 | UC01, UC02, UC03, UC04, UC05, UC06 | Sayli Deshmukh and Vivek Subramonian | 5 | Yes | TE3001, TE1004 | __ | Bill of materials has been made. Hadware is set up and running. | Hardware Requirement
REQ - 303 | Power | _ | The system shall be powered by a separate battery. Test ID: TE3002 | __ | Sayli Deshmukh and Vivek Subramonian | 5 | Yes | TE3002 | __ |  | Hardware Requirement
REQ - 304 | Capturing rate | _ | The camera used in the system shall capture signs regardless of speed of the car. | __ | Sayli Deshmukh and Vivek Subramonian | 1 | No | __ | __ |  | Not a main requirement

## Use cases
Use Cases
Use case ID: | UC01 | Use case ID: | UC03 | Use case ID: | UC05 | Use case ID: | UC07
Primary Actors: | The driver | Primary Actors: | The driver | Primary Actors: | The driver | Primary Actors: | The driver
Secondary Actors: | The system | Secondary Actors: | The system | Secondary Actors: | The system | Secondary Actors: | The system
Pre-Conditions: | System must have a camera attached to it. | Pre-Conditions: | System must have a camera attached to it. | Pre-Conditions: | System must have a camera attached to it. | Pre-Conditions: | System must have a camera attached to it.
Main Success scenario: | Detecting straight lane lines by masking all the noises. | Main Success scenario: | To detect signs and lane lines while driving in the highway. | Main Success scenario: | To detect signs and lane lines while driving on the road of a rural outskirts. | Main Success scenario: | To detect signs and lane lines after switching the lanes.
Use case ID: | UC02 | Use case ID: | UC04 | Use case ID: | UC06 | Use case ID: | UC08
Primary Actors: | The driver | Primary Actors: | The driver | Primary Actors: | The driver | Primary Actors: | The driver
Secondary Actors: | The system | Secondary Actors: | The system | Secondary Actors: | The system | Secondary Actors: | The system
Pre-Conditions: | System must have a camera attached to it. | Pre-Conditions: | System must have a camera attached to it. | Pre-Conditions: | System must have a camera attached to it. | Pre-Conditions: | System must have a camera attached to it.
Main Success scenario: | Detecting all major road signs by masking all the noises. | Main Success scenario: | To detect signs and lane lines while driving on the road of a city. | Main Success scenario: | To detect signs and lane lines while driving during the day time. | Main Success scenario: | To detect signs and lane lines in all weather conditions.

## Mandatory Signs
Mandatory signs
S.no | Sign | Sign Name
1) |  | Stop
2) |  | Road ends.
3) |  | Speed limit
4) |  | Turn
5) |  | Keep to a lane
6) |  | Give way.
7) |  | Cars not allowed
8) |  | No entry

## Pracautionary signs
Precautionary signs
S.no | Sign | Sign Name
1) |  | Bumpy road
2) |  | Children crossing
3) |  | Narrow road
4) |  | Cycle lane
5) |  | Slippery road
6) |  | Work in progress
7) |  | Pedestrian crossing
8) |  | Traffic lights ahead
9) |  | Sharp turn ahead
10) |  | Deer crossing.
11) |  | No parking

## risk matrix
RISK MATRIX
Risk Number | Risk Description | Impact of Risk | Probality of Occurrence | Impact Score | Mitigation Strategy | Domain
R1 | Failure of Camera | Can lead to accidents due to non-capture of signs and line. | 0.2 | 3 | Switch to manual mode. | Hardware
R2 | Rainy or snowy conditions while driving | Can be fatal to the system due to water intrusion. Also line detection can be an issue. | 0.8 | 3 | The system must be in a waterproof box. Do no use to it to drive in rainy and swony conditions. | Hardware
R3 | Overheating of the system processor | Can potentially damage the processor in the system. | 0.9 | 1 | Proper heat dissipation methods such as heat sink shall be installed to minimaized the hating effect. | Hardware
R4 | Inaccurate detection of lane line | Can lead the car to go off the road. | 0.3 | 3 | Autonomous driving should be done only when there is adequate lighting is available. | Software
R5 | Inaccurate detection of road signs. | Can lead to accidents. | 0.4 | 3 | By training the software to detect the signals with the threshold of 85% accuracy | Software
R6 | Processor failure | Can lead to the crash of the system. | 0.15 | 3 | Regular inspections are needed. | Hardware.
R7 | Entire Software failure | Can lead to the crash of the whole system. | 0.25 | 3 | Regular inspections and periodic updates are needed. Testing of the software according to the test strategies. | Software.
1 - LOW
2 - MEDIUM
3 - HIGH