## Cover Sheet
2020-11-19
System Performance Specification
Project Name: |  | Sign and Line Detection
This documents details all requirements which apply to the system. All items are listed with Title, Description, Status etc. This document is updated on weekly basis enlisting item performed during the week.
Document updates:
Sl Nr./ Version | Title | Short description of changes | Author | Date
1 | Draft | Initial version | Vivek Subramonian | 2020-11-11
2 | Draft | Making the requirements more atomic that is splitting down the requirements. | Vivek Subramonian | 2020-11-19
3 | Draft | Marking the priority and functionality of all the requirements | Vivek Subramonian | 2020-12-01
4 | Draft | Addition of Use cases | Vivek Subramonian | 2020-12-24
5 | Draft | Updation of Status in the requirements documents | Vivek Subramonian | 2021-01-02
6 | Draft | Addition of final requirements in the requirements documents. | Vivek Subramonian | 2021-01-11
7 | Final | Freezing of Requirements and use cases. | Vivek Subramonian

## Requirements
Req.ID | Feature | Requirement | Use Case ID | Responsibilty | Priority | Functional Req. ? | Associated Test ID | % Maturity | Remark/Status | Domain
REQ-101 | Line Detection | The system shall detect lane lines that is middle, side and dotted lines on the roads. | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1001 | 100% | Got a working model. Sucessfully detecting our objective which are lane lines. | Main Requirement
REQ-102 | Straight line | The line detection system shall detect stright continous lane lines on either side of the road. | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1002 | 0 | As of now Canny filter seems to be more effective | Main Requirement
REQ-103 | Region of Interest | The line detection system shall correctly identify and detect the Region Of Interest(ROI). | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1002 | 100% | Correctly idetnifying the ROI which in this case the road. | Main Requirement
REQ-104 | Object detection | The system shall specifically detect the lane which it is travelling and ignore all background objects other than the lane lines and sign boards. | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1003 | 100% | Lane lines have been isolated. | Main Requirement
REQ-105 | Masking of noises | The system shall mask the background noises to accurately detect the lane line and sign boards. | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1003 | 100% | Background noises have been masked to an extent. | Main Requirement
REQ-106 | Switching lanes | The system shall recognize lane switching, thereby continuing to detect proper lane line even after switching. | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1004 | 100% |  | Main Requirement
REQ-107 | Narrow and Wide lanes | The system shall work even while traversing in both narrow and wide lanes. | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1005 | 100% | Detecting both narrow and wide lanes. | Main Requirement
REQ-108 | Detection in highways, city and rural roads. | The system shall work in all types of roads. | UC01, UC03, UC04, UC05, UC06, UC07 | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1006 | 100% | Working well is all manner of roads. | Main Requirement
REQ-109 | Curved lines | The line detection system in the car shall ignore curved lane line on either side of the road. | __ | __ | 1 | Yes | __ | __ |  | Not a main requirement
REQ-110 | Detections under the conditions of shadows | The line detection system in the car shall ignore objects under the influence of shadows | __ | __ | 1 | Yes | __ | __ | Detection with the effect of shadows shall be incorporated at a later date when the software is refined. | Not a main requirement
REQ-201 | Sign Detection | The car shall detect major road and traffic signs on an open straight road. | UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 5 | Yes | TE2001 | 70% | Can detect signs based on colours and recognize them but frame rate a bit slow and choppy. Next step to seprate the signs based on shapes. | Main Requirement
REQ-202 | Major signs | Major road signs such as stop sign, turn signs, one way signs shall be detected by the system. | UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 5 | Yes | TE2002 | 70% |  | Main Requirement
REQ-203 | Pracautionary signs | Pracautionary signs such as keep to a lane signs, slow down signs, caution signs and other such signs on any shape of the sign boards shall be detected by the system. | UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 3 | Yes | TE2003 | 70% |  | Main Requirement
REQ-204 | Multiple signs detection | Shall detect mutiple traffic signs on the road. | UC02, UC03, UC04, UC05, UC06 | Dhanush Lingeswaran, Vivek Subramonian and Sayli Deshmukh | 5 | Yes | TE2004 | 70% |  | Main Requirement
REQ-205 | Traffic light signals | The system shall detect traffic light signals on the road. | __ | __ | 1 | Yes | __ | 0 |  | Not a main requirement
REQ-206 | Speed limit signs | The system shall detect speed limit signs on a particular lane. | This feature is used for detecting speed limit signs. | Dhanush Lingeswaran and Subhaga Kannan | 4 | Yes | TE2005 | 70% |  | Main Requirement
REQ-207 | Digital display signs | The system shall ignore digital display signs. | __ | __ | 1 | __ | __ | __ |  | Not a main requirement
REQ - 208 | Detection Periods | The system shall only capture signs and signals during day time when there is sunlight available. | UC03, UC04, UC05, UC06 | Dhanush Lingeswaran and Subhaga Kannan | 4 | Yes | TE2006 | 100% |  | Main Requirement
REQ-209 | Night time detection | The system shall detect signs and lane lines even during the night provided sufficient lighting condiotions are provided. | UC01,UC02, UC03, UC04, UC05, UC06 | All team members. | 1 | Yes | T2007 | 70% |  | Not a requirement
REQ - 301 | Modularity and portability | The hardware system used for the detection process shall be modular and portable to fit in all major sizes of car. | __ | Sayli Deshmukh and Vivek Subramonian | 5 | Non Functional | __ | 0 |  | Hardware Requirement
REQ - 302 | Camera | The camera used in the system shall capture at the rate of 24 frames per second provided the camera is properly mounted. | UC01, UC02, UC03, UC04, UC05, UC06 | Sayli Deshmukh and Vivek Subramonian | 5 | Yes | TE3001 | 20% | Bill of materials has been made. Hadware is set up and running. Yet to start testing. | Hardware Requirement
REQ - 303 | Power | The system shall be powered by a separate battery. | __ | Sayli Deshmukh and Vivek Subramonian | 5 | Yes | TE3002 | 0 |  | Hardware Requirement
REQ - 304 | Capturing rate | The camera used in the system shall capture signs regardless of speed of the car. | __ | Sayli Deshmukh and Vivek Subramonian | 1 | No | __ | __ |  | Not a main requirement

## Use cases
Use Cases
Use case ID: | UC01 | Use case ID: | UC03 | Use case ID: | UC05 | Use case ID: | UC07
Primary Actors: | The driver | Primary Actors: | The driver | Primary Actors: | The driver | Primary Actors: | The driver
Secondary Actors: | The system | Secondary Actors: | The system | Secondary Actors: | The system | Secondary Actors: | The system
Pre-Conditions: | System must have a camera attched to it. | Pre-Conditions: | System must have a camera attched to it. | Pre-Conditions: | System must have a camera attched to it. | Pre-Conditions: | System must have a camera attched to it.
Main Success scenario: | Detecting straight lane lines by masking all the noises. | Main Success scenario: | To detect signs and lane lines while driving in the highway. | Main Success scenario: | To detect signs and lane lines while driving on the road of a rural outskirts. | Main Success scenario: | To detect signs and lane lines after switching the lanes.
Use case ID: | UC02 | Use case ID: | UC04 | Use case ID: | UC06
Primary Actors: | The driver | Primary Actors: | The driver | Primary Actors: | The driver
Secondary Actors: | The system | Secondary Actors: | The system | Secondary Actors: | The system
Pre-Conditions: | System must have a camera attched to it. | Pre-Conditions: | System must have a camera attched to it. | Pre-Conditions: | System must have a camera attched to it.
Main Success scenario: | Detecting all major road signs by masking all the noises. | Main Success scenario: | To detect signs and lane lines while driving on the road of a city. | Main Success scenario: | To detect signs and lane lines while driving during the day time.