## cover sheet
Acceptance test plan for Line and Sign detection for Autonomous Driving (Group II)
Project Information
Project name: | Line and Sign detection for Autonomoums Driving (Group II)
Reference Document: | Project requirement Specification document Version 1.1
Test document created by: | Saranyaa Suresh
Project Start date: | 2020-10-27
Estimated completion date: | 2021-02-11
Project Status: | On Track

## Table of contents
1.Table of contents
Sl.no | Topics
1 | Introduction
2 | Test environment
3 | Test cases

## Introduction
2.Introduction and Purpose of the Document
The purpose of this document is to specify the test cases for the project Line and sign detection
2.1 Document Overview
The document has been segmented for easy reference. The table below provides user with an overview of the contents of each section:
Section | Contents
1) Cover sheet | This section contains the document change history information.
2) Introduction and purpose of document | A brief descrpition about the test document.
3) Test Environment | This section describes the Test Environment setup and Configuration tools details.
4) Test cases | This section contains our Test Case procedures which are going to be executed on the raspberry pi.

## Test environment
3. TEST ENVIRONMENT
3.1 TEST ENVIRONMENT Evaluation board : A raspberry pi 4 RAM and Memory: 8GB and 64GB Software required: Python with Opencv and Tensorflow modules. Required Hardware Tools: 1. Raspberry pi and camera 2. Keyboard 3. A 3.4 inch Touchscreen monitor. 4. A portable power bank.

## Test Case
4. TEST CASES
Test Case ID | Test Case | Pre conditions | Test Procedure |  | Expected Result | Sample Test Video | Result | [9 empty] | Final Result | Comments (if any)
[7 empty] | TestVideo1 | TestVideo2 | TestVideo3 | TestVideo4 | TestVideo5 | TestVideo6 | TestVideo7 | TestVideo8 | TestVideo9 | TestVideo10
Autobahn
Video File input to Raspberry pi
TE1001 | To test if the system detects the straight continous lanes. | •The video file input is fed into Raspberry pi. | Step1 | Launch and run the python script: Lane_Detection_TestingModule.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video3.mp4 test_video1.mp4 test_video2.mp4 test_video5.m4v test_video7.mp4 | PASS 86% | PASS 98% | PASS 86% | NA | PASS 96% | NA | PASS 92% | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the straight continous lane lines. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from testvideo2 Total Frame=211 Frames with 2 Lanes=196 Frames with 1 Lanes=14 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1002 | To test if the system detects the Dashed lanes. | •The video file input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video3.mp4 test_video1.mp4 test_video2.mp4 test_video5.mp4 test_video7.mp4 test_video8.mp4 | PASS 86% | PASS 98% | PASS 86% | NA | PASS 96% | NA | PASS 92% | PASS 94% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the straight Dashed lane lines. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 2 Total Frame=211 Frames with 2 Lanes=196 Frames with 1 Lanes=14 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1003 | To test if the system masks the background noise and no wrong objects are detected other than lane line and sign boards. | •The video file input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video1.mp4 test_video2.mp4 test_video3.mp4 test_video4.mp4 test_video5.mp4 test_video6.mp4 test_video7.mp4 (shadow was detetcted once) test_video8.mp4 test_video9.mp4(shadow are detected) test_video10.mp4 | PASS | PASS | PASS | PASS | PASS (One wrong objects were detected) | PASS | PASS (One wrong objects were detected) | PASS | FAIL | PASS (Two wrong objects were detected) |  | Not tested for sign Detection
|  |  | Step2 | Visually Inspect the output screen and count if it detects any wrong object other than lane line and sign boards. | Ignore if two or less wrong objects are detected. Then the test is considred to be pass.
TE1004 | To test if the system works as per seelcted region of interest. | •The video input is fed into Raspberry pi. •The system should work with previous region of interest, if the user does not want to change the calibration. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video1.mp4 test_video2.mp4 test_video3.mp4 test_video4.mp4 test_video5.mp4 test_video6.mp4 test_video7.mp4 test_video8.mp4 test_video9.mp4 test_video10.mp4 | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS |  | The accuracy of detected lanes depend on the selection of ROI
|  |  | Step2 | To select special mode region of interest, give input 's'. | Calibration mode Activated.
|  |  | Step3 | Select required region of interest in the calibration mode. | The red box will indicate previous ROI. The selected ROI is indicated by blue box.
|  |  | Step4 | Visually inspect whether the red box is updated to the selected ROI. | The lane lines are detected in the specified ROI.
TE1005 | To test if the system detects lane line and sign boards under shadow condition. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video9.mp4 | NA | NA | NA | NA | NA | NA | NA | NA | FOR LANE AND SIGN DETECTION:FAIL 44% | NA
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under shadow. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 9 Total Frame=1200 Frames with 2 Lanes=511 Frames with 1 Lanes=671 Frames with No Lanes=17
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1006 | To test if the system detects lane and sign during Different Day light Condition. Refer Defintions for different daylight condition. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video1.mp4 test_video2.mp4 test_video3.mp4 test_video4.mp4 test_video5.mp4 test_video6.mp4 test_video7.mp4 test_video9.mp4 test_video10.mp4 | PASS 86% | PASS 96% | PASS 86% | PASS 85% | PASS 96% | PASS 89% | PASS 92% | NA | FAIL 45% | PASS 95% |  | Not tested for sign Detection
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under different daylight condition. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 2 Total Frame=211 Frames with 2 Lanes=196 Frames with 1 Lanes=14 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1007 | To test if the system detects lane line and sign boards during night time. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video8.mp4 | NA | NA | NA | NA | NA | NA | NA | FOR LANE DETECTION:PASS 92% FOR SIGN DETECTION: PASS 83% | NA | NA
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under night condition. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 8 Total Frame=527 Frames with 2 Lanes=486 Frames with 1 Lanes=40 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1008 | To test if the system detects during different weather conditions. Refer Definitions for different weather Conditions used for testing. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under different weather condition. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | Total Frame = Frames with 2 lanes=
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1009 | To test if the system could detect Narrow Lanes of 2.5 to 3.5m. Refer the Definitions for Narrow lane. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Narrow lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | Total Frame = Frames with 2 lanes=
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1010 | To test if the system could detect Wider Lanes of 3.7m and above. Refer definitions for the Wider lanes used for testing. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video6.mp4 test_video1.mp4 test_video4.mp4 test_video5.mp4 test_video7.mp4 test_video8.mp4 | PASS 82% | NA | NA | PASS 80% | PASS 94% | PASS 82% | PASS 86% | PASS 94% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Wider lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 6 Total Frame=828 Frames with 2 Lanes=704 Frames with 1 Lanes=123 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 80% and above, then test is considred to be successful.
TE1011 | To test if the system works during sudden switching of lane(eg:overtaking) Refer Definitions for sudden change of lane. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video4.mp4 test_video6.mp4 | NA | NA | NA | PASS 82% | NA | PASS 89% | NA | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights when there is sudden change of lane.. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 6 Total Frame=828 Frames with 2 Lanes=704 Frames with 1 Lanes=123 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 80% and above, then test is considred to be successful.
TE1012 | To test if the system could detect horizontal curved lanes. Refer Definitions for Horizontal curved lanes. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video7.mp4 test_video1.mp4 test_video10.mp4 | PASS 84% | NA | NA | NA | NA | NA | PASS 92% | NA | NA | PASS 92%
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the horizontal curved lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 7 Total Frame=1261 Frames with 2 Lanes=1171 Frames with 1 Lanes=75 Frames with No Lanes=14
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 85% and above, then test is considred to be successful.
TE1013 | To test if the system could detect steep curved lanes. | •The video input is fed into Raspberry pi. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video9.mp4 | NA | NA | NA | NA | NA | NA | NA | NA | FAIL 44% | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the steep curved lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 9 Total Frame=1200 Frames with 2 Lanes=511 Frames with 1 Lanes=671 Frames with No Lanes=17
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 80% and above, then test is considred to be successful.
SIGN DETECTION - Method 1
TE2001 | To test if the system detects the Major road signs - TURN RIGHT SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video5.mp4 | NA | NA | NA | NA | PASS 70% | NA | NA | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and classified as "TURN RIGHT".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2002 | To test if the system detects the Major road signs - TURN LEFT SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and classified as "TURN LEFT".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2003 | To test if the system detects the Major road signs -PRIORITY ROAD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video3.mp4 test_video2.mp4 | NA | PASS 75% | PASS 80% | NA | NA | NA | NA | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and classified as " PRIORITY ROAD"
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2004 | To test if the system detects the Major road signs- ROAD ENDS SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and classified as "ROAD ENDS SIGN BOARD".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2005 | To test if the system detects the Major road signs-NO PASSING SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video3.mp4 test_video2.mp4 test_video5.mp4 test_video8.mp4 | NA | PASS 75% | PASS 80% | NA | PASS 60% | NA | NA | PASS 83% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and classified as "NO PASSING SIGN BOARD".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2006 | To test if the system detects the Major road signs-EXIT SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and classified as "EXIT SIGN BOARD".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2007 | To test if the system detects the Major road signs - KEEP RIGHT SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video8.mp4 | NA | NA | NA | NA | NA | NA | NA | PASS 83% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road signs. | The road sign is identified and classified as "KEEP RIGHT".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2008 | To test if the system detects the Precautionary road signs - PROHIBITORY SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Precautionary road signs. | The road sign is identified and classified as "PROHIBITORY SIGN BOARD.".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2009 | To test if the system detects the Precautionary road signs - SLIPPERY ROAD SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Precautionary road signs. | The road sign is identified and classified as "TURN RIGHT".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2010 | To test if the system detects the Precautionary road signs - ROAD WORK SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Precautionary road signs. | The road sign is identified and classified as "SLIPPERY ROAD SIGN BOARD".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2011 | To test if the system detects the Major road signs - End of all speed and passing limits | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video5.mp4 | NA | NA | NA | NA | PASS 60% | NA | NA | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road signs. | The road sign is identified and classified as " End of all speed and passing limits".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2012 | To test if the system detects the Precautionary road signs - Wild animals crossing | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video3.mp4 | NA | NA | PASS 80% | NA | NA | NA | NA | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Precautionary road signs. | The road sign is identified and classified as "Wild animals crossing".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2013 | To test whether the system detects the digital Display signals - DIGITAL SPEED LIMIT SIGNS. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Digital Speed limit sign. | The road sign is identified and classified as "DIGITAL SPEED LIMIT SIGNS".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2014 | To test whether the system detects the Speed limit signs - 70km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video3.mp4 test_video2.mp4 test_video8.mp4 | NA | PASS 75% | PASS 80% | NA | NA | NA | NA | PASS 83% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights theSpeed limit sign. | The road sign is identified and classified as "70km/h".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2015 | To test whether the system detects the Speed limit signs - 120km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video5.mp4 test_video6.mp4 test_video8.mp4 | NA | NA | NA | NA | PASS 60% | FAIL 25% | NA | PASS 83% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Speed limit sign. | The road sign is identified and classified as "120km/h".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2016 | To test whether the system detects the Speed limit signs - 130km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Speed limit sign. | The road sign is identified and classified as "130km/h".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2017 | To test whether the system detects the Speed limit signs - 80km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Speed limit sign. | The road sign is identified and classified as "80km/h".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2018 | To test if the system could detect multiple signs | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | test_video5.mp4 test_video3.mp4 test_video8.mp4 | NA | NA | PASS 80% | NA | PASS 60% | NA | NA | PASS 83% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Multiple sign board. | The multiple road sign has to be identified and classified.
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2019 | To test if the system could Recogonize Faded or damaged sign boards. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether the system could recogonize the sign boards. | The road sign has to be Recogonized.
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
TE2020 | To test if the system could detect Traffic Light signals. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the python script Sign_Detection_Integrated_Video.py in the command line. | Launched and script is processed, the video will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Traffic Light signals. | The road sign is identified as "Traffic Light signals".
|  |  | Step3 | Manually calculate accuracy of the system by counting total number of boards and with the number of boards detected. | If the system can detect and highlight major road signs with an accuracy of 60% and above, then test is considred to be successful.
SIGN DETECTION - Method 2
TE2001 | To test if the system detects the Major road signs - TURN RIGHT SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2002 | To test if the system detects the Major road signs - TURN LEFT SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2003 | To test if the system detects the Major road signs - STRAIGHT AHEAD SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2004 | To test if the system detects the Major road signs- ROAD ENDS SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2005 | To test if the system detects the Major road signs-NO ENTRY SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2006 | To test if the system detects the Major road signs-EXIT SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2007 | To test if the system detects the Precautionary road signs - PROHIBITORY SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2008 | To test if the system detects the Precautionary road signs - NO PASSING SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2009 | To test if the system detects the Precautionary road signs - SLIPPERY ROAD SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2010 | To test if the system detects the Precautionary road signs - ROAD WORK SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2011 | To test if the system detects the Precautionary road signs - NARROW ROAD SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2012 | To test if the system detects the Precautionary road signs - PEDESTRAIN CROSSING SIGN BOARD. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2013 | To test whether the system detects the digital Display signals - DIGITAL SPEED LIMIT SIGNS. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2014 | To test whether the system detects the Speed limit signs - 50km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2015 | To test whether the system detects the Speed limit signs - 120km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2016 | To test whether the system detects the Speed limit signs - 130km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2017 | To test whether the system detects the Speed limit signs - 80km/h. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2018 | To test if the system could detect multiple signs | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2019 | To test if the system could Recogonize Faded or damaged sign boards. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
TE2020 | To test if the system could detect Traffic Light signals. | •The video input is fed into Raspberry pi. | Step1 | Launch and run the Tensorflow in the command line. | Launched and script is processed, the video will be displayed in the output screen.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Major road sign. | The road sign is identified and highlighted.
Step3
|  |  | Step4 | Manually check accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight major road signs with an accuracy of 85% and above, then test is considred to be successful.
Camera input to Raspberry pi
TE1014 | To test if the system detects the straight continous lanes. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, the video will be displayed in the output screen. | test_video3.mp4 test_video1.mp4 test_video2.mp4(one wrong object detected) test_video5.m4v test_video7.mp4 | PASS 76% | PASS 86% | PASS 84% | NA | PASS 85% | NA | PASS 87% | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the straight continous lane lines. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video3 Total Frame=472 Frames with 2 Lanes=399 Frames with 1 Lanes=73 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1015 | To test if the system detects the Dashed lanes. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video3.mp4 test_video1.mp4 test_video2.mp4 test_video5.m4v test_video6.m4v test_video7.mp4 test_video8.mp4 | PASS 76% | PASS 86% | PASS 84% | NA | PASS 85% | PASS 76% | PASS 89% | PASS 86% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the straight Dashed lane lines. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video3 Total Frame=472 Frames with 2 Lanes=399 Frames with 1 Lanes=73 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1016 | To test if the system masks the background noise and no wrong objects are detected other than lane line and sign boards. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video1.mp4 test_video2.mp4 test_video3.mp4 test_video4.mp4 test_video5.mp4 test_video6.mp4 test_video7.mp4 (shadow was detetcted once) test_video8.mp4 test_video9.mp4(shadow are detected) test_video10.mp4 | PASS (One wrong objects were detected) | PASS | PASS | PASS (one wrong objects were detected) | PASS (Two wrong objects were detected) | PASS | PASS (One wrong objects were detected) | PASS | FAIL | PASS (Two wrong objects were detected) |  | Not tested for sign Detection
|  |  | Step2 | Visually Inspect the output screen and count if it detects any wrong object other than lane line and sign boards. | Ignore if two or less wrong objects are detected.Then the test is considred to be pass.
TE1017 | To test if the system works as per seelcted region of interest. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. •The system should work with previous region of interest, if the user does not want to change the calibration. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video1.mp4 test_video2.mp4 test_video3.mp4 test_video4.mp4 test_video5.mp4 test_video6.mp4 test_video7.mp4 test_video8.mp4 test_video9.mp4 test_video10.mp4 | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS |  | The accuracy of detected lanes depend on the selection of ROI
|  |  | Step2 | To select special mode region of interest, give input 's'. | Calibration mode Activated.
|  |  | Step3 | Select required region of interest in the calibration mode. | The red box will indicate previous ROI. The selected ROI is indicated by blue box.
|  |  | Step4 | Visually inspect whether the red box is updated to the selected ROI. | The lane lines are detected in that specified ROI.
TE1018 | To test if the system detects lane line and sign boards under shadow condition. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video9.mp4 | NA | NA | NA | NA | NA | NA | NA | NA | FAIL 50% | NA |  | Not tested for sign Detection
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under shadow. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example rom test video 9 Total Frame=1112 Frames with 2 Lanes=573 Frames with 1 Lanes=526 Frames with No Lanes=13
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1019 | To test if the system detects lane and sign during Different Day light Condition. Refer Defintions for different daylight condition. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video1.mp4 test_video2.mp4 test_video3.mp4 test_video4.mp4 test_video5.mp4 test_video6.mp4 test_video7.mp4 test_video9.mp4 test_video10.mp4 | PASS 76% | PASS 86% | PASS 84% | PASS 76% | PASS 85% | PASS 76% | PASS 87% | NA | FAIL 48% | PASS 87% |  | Not tested for sign Detection
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under different daylight condition. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video3 Total Frame=472 Frames with 2 Lanes=399 Frames with 1 Lanes=73 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1020 | To test if the system detects lane line and sign boards during night time. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video8.mp4 | NA | NA | NA | NA | NA | NA | NA | PASS 86% | NA | NA |  | Not tested for sign Detection
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under night condition. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 8 Total Frame=288 Frames with 2 Lanes=248 Frames with 1 Lanes=40 Frames with No Lanes=0
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1021 | To test if the system detects during different weather conditions. Refer Definitions for different weather Conditions used for testing. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen, if it detects and highlights the lane lines and sign boards under different weather condition. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | Total Frame = Frames with 2 lanes=
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1022 | To test if the system could detect Narrow Lanes of 2.5 to 3.5m. Refer the Definitions for Narrow lane. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | [12 empty] | Not tested Due to lackof input video.
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Narrow lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | Total Frame = Frames with 2 lanes=
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1023 | To test if the system could detect Wider Lanes of 3.7m and above. Refer definitions for the Wider lanes used for testing. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video6.mp4 test_video1.mp4 test_video4.mp4 test_video5.mp4 test_video7.mp4 test_video8.mp4 | PASS 75% | NA | NA | PASS 77% | PASS 86% | PASS 75% | PASS 88% | PASS 87% | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the Wider lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 4 Total Frame=627 Frames with 2 Lanes=469 Frames with 1 Lanes=156 Frames with No Lanes=2
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1024 | To test if the system works during sudden switching of lane(eg:overtaking) Refer Definitions for sudden change of lane. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video4.mp4 test_video6.mp4 | NA | NA | NA | PASS 77% | NA | PASS 76% | NA | NA | NA | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights when there is sudden change of lane.. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 4 Total Frame=627 Frames with 2 Lanes=483 Frames with 1 Lanes=142 Frames with No Lanes=2
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1025 | To test if the system could detect horizontal curved lanes. Refer Definitions for Horizontal curved lanes. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video7.mp4 test_video1.mp4 test_video10.mp4 | PASS 78% | NA | NA | NA | NA | NA | PASS 88% | NA | NA | PASS 87%
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the horizontal curved lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 7 Total Frame=513 Frames with 2 Lanes=456 Frames with 1 Lanes=17 Frames with No Lanes=103
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.
TE1026 | To test if the system could detect steep curved lanes. | • Display the input Video file on a separate monitor. • Focus the Camera to the monitor. | Step1 | Repeat Step1 from test TE1001 | Launched and script is processed, it will be displayed in the output screen. | test_video9.mp4 | NA | NA | NA | NA | NA | NA | NA | NA | FAIL 50% | NA
|  |  | Step2 | Visually Inspect the output screen,whether it detects and highlights the steep curved lanes. | Both the lanes should be detected.
|  |  | Step3 | At the end of the video, take note of total frames,number of frames with 2,1 and no lanes are detected. | The results will be displayed after the each test video.For example from test video 9 Total Frame=1112 Frames with 2 Lanes=573 Frames with 1 Lanes=526 Frames with No Lanes=13
|  |  | Step4 | Manually calculate accuracy of the system by using total number of frames and frames with 2 lanes. | If the system can detect and highlight lanes lines with an accuracy of 75% and above, then test is considred to be successful.

## Definitions
Definition |  | Test video or Image | Remarks(if any)
Day light | Too bright | NA | Test not conducted due to lack of video input.
| Less bright | test_video1.mp4,test_video4.mp4
| Dull weather | test_video3.mp4
Sudden Change of line |  | test_video6.mp4 (13sec to 17sec, test_video4.m4v(4 sec to 6 sec)
Horizontal curve |  | test_video5.m4v
Steep curved Lanes |  | test_video9.mp4
Narrow road |  |  | Test not conducted due to lack of video input.
Wide road |  | test_video6.m4v
weather Conditions | snow | NA | Test not conducted due to lack of video input.
| Rain | NA

## Sheet1 (hidden)
4. Test Cases
Test case ID | Test case | Test Procedure | Sample Test Videos | Criteria for successful test | Actual output | Result | Remarks(if any)
Autobahn
Video input to the Raspberry pi
TE1001 | To test if the system detects the straight lanes. | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect the Output Screen, whether it detects and highlights the Straight Continous lane lines. |  | When the system can detect and highlight the lane lines with an accuracy of 85 and above, then it is considred to be successful for this particular test. | Detection of Straight Lanes. | Pass
TE1002 | To test if the system detects the dotted lanes. | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect the Output Screen, whether it detects and highlights the Dotted lane lines. |  | When the system can detect and highlight the lane lines with an accuracy of 85 and above, then it is considred to be successful for this particular test. | Detection of dotted Lanes. | Pass
TE1003 | To test if the system detects any objects other than lane line and Sign boards. | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect the Output Screen and count if it detects any wrong object other than lane line and sign boards. •Ignore if the count of wrong objects are 2 or less. |  | When the system detects any other objects other than sign boards and lane lines, if number of wrong objects detected are 2 or less than that then the test is considered to be successful. | Detection of Lanes | Pass | Not tested for sign Detection.
TE1004 | To test if there is clear Visibility of the lane and sign boards to ensure the performance of camera | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect the Output Screen whether the lanes and sign boards are properly focused by camera. |  | The video captured by the camera should not be blur, the lane lines and sign boards should be clearly visible, then the test is successful.
TE1005 | To test if the system works as per selected region of interest. | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •To select special mode Region of interest, give input 's' •In calibration mode, select the required ROI. •Visually Inspect if it detects lane line in the specified ROI. |  | In calibration mode,user should able to select the region of interest. The system should properly detect the lane in the selected ROI. •If the user does not select the calibration mode, it should work with the previous region of interest. | Detection of Lanes in the selected ROI. | Pass
TE1006 | To test if the system detects under Shadow condition for lane and sign detection | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect if it detects lane line during shadow condition in the test video………. |  | When the system can detect and highlight the lane lines with an accuracy of 85 and above during shadow condition, then it is considred to be successful for this particular test. |  |  | Not tested for sign Detection.
TE1007 | To test if the system detects lane and sign during Day light | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect if it detects lane line during different day light condition in the test video………. |  | When the system can detect and highlight the lane lines with an accuracy of 85 and above during different daylight condition, then it is considred to be successful for this particular test. | Detection of lane | Pass | Not tested for sign Detection.
TE1008 | To test if the system detects lane and sign during Night light. | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect if it detects lane line during night condition in the test video |  | When the system can detect and highlight the lane lines with an accuracy of 85 and above during night condition, then it is considred to be successful for this particular test. | Detection of lane | Pass | Not tested for sign Detection.
TE1009 | To test the system during different weather conditions. | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect if it detects lane line during different weather condition. |  | When the system can detect and highlight the lane lines with an accuracy of 85 and above during different weather condition, then it is considred to be successful for this particular test. |  |  | Test not conducted due to lack of input video.
•Check if the system detects lane during snow.
•Check if the system detects lane during rain.
TE1010 | To test if the system works for different width of the road. | •The video input is fed into Raspberry pi. •The code is processsed in Raspberry pi. •Visually Inspect if it detects lane line at different width of the road as specified in the test case. |  | When the system can detect and highlight the lane lines with an accuracy of 85 and above at different width of the road, then it is considred to be successful for this particular test. | Detection of Lane | Pass
| •Check if the system detects wider lanes of 3.75m. |  |  |  | Detection of wider Lanes | Pass
•Check if the system detects Narrow lanes of 2.5to 3.5m.
TE1011 | To test if the system works during sudden change of lane.
TE1012 | To test if the system could detect the curved lanes