## Cover Sheet
2020-11-19
System Performance Specification
Project Name: |  | Sign and Line Detection
This document provides the requirements for the system
This documents details all requirements which apply to the system. All items are listed with Title, Description, Status etc. This document is updated on weekly basis enlisting item performed during the week.
Document updates
Sl Nr./ Version | Title | Short description of changes | Author | Date
1 | Draft | Initial version | Vivek Subramonian | 2020-11-11
2 | Draft | Making the requirements more atomic that is splitting down the requirements. | Vivek Subramonian | 2020-11-19
3 | Draft
4 | Draft
5 | Draft
6 | Draft
7 | Draft
8 | Draft
9 | Draft
10 | Draft
11 | Final

## Requirements
Req.ID | Feature | Requirement | Responsibilty | Priority | Functional Req. ? | Associated Test ID | % Maturity | Remark | Domain
REQ-101 | Line Detection | The car shall detect lane lines that is middle, side and dotted lines on the roads. | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1001 | 10% | Implemented various filtering techniques | Main Requirement
REQ-102 | Straight line | The line detection system in the car shall detect stright lane lines on either side of the road. | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1002 | 0 | As of now Canny filter seems to be more effective | Main Requirement
REQ-103 | Object detection | The system shall specifically detect the lane which it is travelling and ignore all background objects other than the lane lines and sign boards. | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1003 | 10% | Lane lines have been isolated. | Main Requirement
REQ-104 | Masking of noises | The system shall mask the background noises to accurately detect the lane line and sign boards. | Juliet Eldo and Saranya Suresh | 5 | Yes | TE1003 | 10% | Background noises have been masked to an extent. | Main Requirement
REQ-105 | Curved lines | The line detection system in the car shall ignore curved lane line on either side of the road. | __ | 1 | Yes | __ | __ |  | Not a main requirement
REQ-106 | Detections under the conditions of shadows | The line detection system in the car shall ignore objects under the influence of shadows | __ | 1 | Yes | __ | __ | Detection with the effect of shadows shall be incorporated at a later date when the software is refined. | Not a main requirement
REQ-201 | Sign Detection | The car shall detect major road and traffic signs on an open straight road. | Dhanush Lingeswaran and Subhaga Kannan | 5 | Yes | TE2001 | 10% | Accquired the necessary data sets. Beginning to work on training the model | Main Requirement
REQ-202 | Major signs | Major road signs such as stop sign, turn signs, one way signs shall be detected by the system. | Dhanush Lingeswaran and Subhaga Kannan | 5 | Yes | TE2002 | 0 |  | Main Requirement
REQ-203 | Pracautionary signs | Pracautionary signs such as keep to a lane signs, slow down signs, caution signs and other such signs on any shape of the sign boards shall be detected by the system. | Dhanush Lingeswaran and Subhaga Kannan | 3 | Yes | TE2003 | 0 |  | Main Requirement
REQ-204 | Traffic light signals | The system shall detect traffic light signals on the road. | Dhanush Lingeswaran and Subhaga Kannan | 2 | Yes | TE2004 | 0 |  | Main Requirement
REQ-205 | Speed limit signs | The system shall detect speed limit signs on a particular lane. | Dhanush Lingeswaran and Subhaga Kannan | 4 | Yes | TE2005 | 0 |  | Main Requirement
REQ-206 | Digital display signs | The system shall ignore digital display signs. | __ | 1 | __ | __ | __ |  | Not a main requirement
REQ - 207 | Detection Periods | The system shall only capture signs and signals during day time when there is sunlight available. | Dhanush Lingeswaran and Subhaga Kannan | 4 | Yes | TE2006 | 0 |  | Main Requirement
REQ-208 | Night time detection | The system shall ignore signs and signals during the night. | Dhanush Lingeswaran and Subhaga Kannan | 1 | No | __ | __ |  | Not a requirement
REQ - 301 | Modularity and portability | The hardware system used for the detection process shall be modular and portable to fit in all major sizes of car. | Sayli Deshmukh and Vivek Subramonian | 5 | Non Functional | __ | 0 |  | Hardware Requirement
REQ - 302 | Camera | The camera used in the system shall capture at the rate of 24 frames per second. | Sayli Deshmukh and Vivek Subramonian | 5 | Yes | TE3001 | 10% | Bill of materials has been made. | Hardware Requirement
REQ - 303 | Power | The system shall be powered by a separate battery. | Sayli Deshmukh and Vivek Subramonian | 5 | Yes | TE3002 | 0 |  | Hardware Requirement
REQ - 304 | Capturing rate | The camera used in the system shall capture signs regardless of speed of the car. | Sayli Deshmukh and Vivek Subramonian | 1 | No | __ | __ |  | Not a main requirement